## PPP Projects
Job Number | Project Description | District | Route | Section | County | Scope | Letting Date | Due to PM | 1st Review Sent to SB | 1st Review Returned from SB | 1st Review Sent to District | 1st Review Returned from District | 2nd Review Sent to SB | 2nd Review Returned from SB | 2nd Review Sent to District | 2nd Review Returned from District | 3rd Review Sent to SB | 3rd Review Returned from SB | 3rd Review Sent to District | 3rd Review Returned from District | 4th Review Sent to SB | 4th Review Returned from SB | 4th Review Sent to District | 4th Review Returned from District | Submittal to SB for CCD | Requested Title Sheet | Received Signed Plans | Sent to CCD | Notes
A10059 | Hwy.49 - Hwy.44 (S) | 1 | 85 | 1 | Philips | Level Up, Chip Seal & Fog Seal; 2' Shoulders | 2026-11-04 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-03 | 2026-09-08 | 2026-09-09 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-23 | 2026-09-23
A20044 | Hwy.165 - Hwy.152 (S) | 2 | 130 | 6 | Arkansas | Level Up & 2" Overlay | 2026-11-04 | 2026-08-17 | 2026-08-25 | 2026-08-27 | 2026-08-27 | 2026-08-28 | 2026-08-28 | 2026-08-29 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-11 | 2026-09-11 | 2026-09-21 | 2026-10-14
A30049 | Hwy.355 - Hwy.278 (S) | 3 | 73 | 0,1, & 2 | Hempstead & Howard | Level Up & 1.5" Overlay (Secs. 0 & 1); 2" Mill & 2" Overlay (Sec. 2) | 2026-11-04 | 2026-08-17 | 2026-08-11 | 2026-08-12 | 2026-08-12 | 2026-08-18 | 2026-08-18 | 2026-08-20 | 2026-08-20 | 2026-08-25 | 2026-08-25 | 2026-08-27 | 2026-08-27 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-08 | 2026-09-08 | 2026-09-09 | 2026-09-10
A40062 | Hwy.8 - South (S) | 4 | 375 | 1 | Polk | Level Up & 2" Overlay; Spot Patching; 2' Shoulders | 2026-11-04 | 2026-08-17 | 2026-08-21 | 2026-08-24 | 2026-08-24 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-04 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-11 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-22 | 2026-09-17
A50033 | Hwy.67B - Hwy.13 (S) | 5 | 367 | 15 | White | Mill & Overlay (LM 2.598-5.406); Level Up & UTBWC (LM 5.406-8.641) | 2026-11-04 | 2026-08-17 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-09-08 | 2026-09-08 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-16 | 2026-09-21 | 2026-09-22
A50052 | Stone Co. Line - Hwy.25 (S) | 5 | 14 | 8 | Independence | 2" Overlay; Spot Leveling | 2026-11-04 | 2026-08-17 | 2026-08-14 | 2026-08-17 | 2026-08-18 | 2026-08-25 | 2026-08-28 | 2026-08-31 | 2026-08-31 | 2026-09-08 | 2026-09-08 | 2026-09-09 | 2026-09-09 | 2026-09-14 | 2026-09-14 | 2026-09-16 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-16 | 2026-09-21 | 2026-09-22
A60066 | Hwy.367 - Hwy.365 (S) | 6 | 338 | 2 | Pulaski | 2" Mill & 2" Overlay (LM 0.00-2.60 & 3.1-5.078); 6" Mill, 4" HiMod & 2" Surface (LM 2.60-3.1) | 2026-11-04 | 2026-08-17 | 2026-08-17 | 2026-08-19 | 2026-08-20 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 2026-09-03 | 2026-09-03 | 2026-09-04 | 2026-09-04 | 2026-09-08 | 2026-09-14 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-17
A70049 | Ouachita River - North (S) | 7 | 167 | 3 | Calhoun | 2" Mill & 2" Overlay | 2026-11-04 | 2026-08-17 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-21 | 2026-09-14
A70050 | Hwy.67 - Hwy.51 (S) | 7 | 182 | 0 | Clark | Leveling, Patching, 3" Overlay; 2' Shoulders | 2026-11-04 | 2026-08-17 | 2026-08-25 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-27 | 2026-08-31 | 2026-08-31 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-03 | 2026-09-03 | 2026-09-03 | 2026-09-04 | 2026-09-04 | 2026-09-09 | 2026-09-11 | 2026-09-14 | 2026-09-23 | 2026-09-23
A80050 | Hwy.95 - Hwy.124 (S) | 8 | 65 | 8 | Van Buren | UTBWC (LM 2.956-10.939); 2" Mill & 2" Overlay (LM 10.939-16.220) | 2026-11-04 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-18 | 2026-08-28 | 2026-08-28 | 2026-08-29 | 2026-08-31 | 2026-09-08 | 2026-09-08 | 2026-09-09 | 2026-09-11 | 2026-09-16 | 2026-09-16 | 2026-09-17 | 2026-09-21 | 2026-09-21 | 2026-09-28 | 2026-09-21 | 9/258/2026 | 2026-09-29
A90050 | Missouri State Line - Hwy.62 (S) | 9 | 101 | 1 | Baxter | 2" Mill & 2" Overlay | 2026-11-04 | 2026-08-17 | 2026-07-30 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-05 | 2026-08-07 | 2026-08-10 | 2026-08-13 | 2026-08-13 | 2026-08-14 | 2026-08-14 | 2026-09-01 | 2026-09-01 | 2026-09-02 | 2026-09-02 | 2026-09-03 | 2026-09-14 | 2026-09-14 | 2026-09-28 | 2026-09-29
A90051 | Hwy.412 Impvts. (Carroll & Madison COS.) (S) | 9 | 412 | 3,4, & 5 | Carroll & Madison | Spot Patching, Spot Leveling & Thin Overlay (1") | 2026-11-04 | 2026-08-17 | 2026-07-30 | 2026-08-05 | 2026-08-05 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-10 | 2026-08-14 | 2026-08-14 | 2026-08-17 | 2026-08-17 | 2026-08-20 | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-01 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-22
A00103 | Monette - Mississippi | 10 | 18 | 4 | Craighead | UTBWC | 2026-11-04 | 2026-08-17 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14
A10058 | Monroe Co. Line - Co. RD. 625 (S) | 1 | 49 | 10 | Philips | Level Up & Chip Seal, 2' Shoulders | 2027-01-20 | 2026-10-26 | 2026-08-21 | 2026-08-25 | 2026-08-25 | 2026-09-01 | 2026-09-02 | 2026-09-06 | 2026-09-09 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-24 | 2026-10-05 | 2026-10-05 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-10-13 |  |  | Send for DE Signature
A10060 | Monroe Co. Line – Co. Rd. 625 (S) | 1 | 218 | 1 | Crittenden | Mill & Overlay | 2027-01-20 | 2026-10-26 | [20 empty] | District is waiting on Mix Design from Materials
A20042 | Hwy. 82 – Louisiana St. Line (Sel. Secs.) (S) | 2 | 35 | 2 | Grant | Level Up & 2" Overlay | 2027-01-20 | 2026-10-26 | [20 empty] | Emailed district with the Reminder for October 26 Submission
A20043 | Saline Co. Line – Hwy. 167B (S) | 2 | 65 | 21 & 22 | Chicot | 2" Overlay; Add 2' Shoulders | 2027-01-20 | 2026-10-26 | [20 empty] | Emailed district with the Reminder for October 26 Submission
A30048 | Hwy. 71 – Howard Co. Line (S) | 3 | 27 | 1 & 2 | Howard & Sevier | 2" Mill & 1.5" Overlay | 2027-01-20 | 2026-10-26 | [20 empty] | Emailed district with the Reminder for October 26 Submission
A30051 | Hwy. 71 – Co. Rd. 28 (S) | 3 | 237 | 1 | Miller | 2" Overlay; 2' Shoulders | 2027-01-20 | 2026-10-26 | [20 empty] | Emailed district with the Reminder for October 26 Submission
A40061 | Oklahoma State Line – Hwy. 71 (S) | 4 | 28 | 1 | Scott | Level Up & UTBWC (LM 0.0-15.86); 2" Mill & 2" Overlay (LM 15.86-20.448) | 2027-01-20 | 2026-10-26 | [20 empty] | Emailed district with the Reminder for October 26 Submission
A50051 | Hwy. 62 – Hwy. 395 (Salem) (S) | 5 | 9 | 15 | Fulton | 2" Mill & 1.5" Overlay; 2' Shoulders | 2027-01-20 | 2026-10-26 | 2026-09-18 | 2026-09-22 | 2026-09-24 | [17 empty] | Emailed Micah asking if it is ready for 2nd review @10.13.26
A50053 | Hwy. 167 – Hwy. 122 (S) | 5 | 14 | 9 & 10 | Independence | Level Up & UTBWC; 2' Shoulders | 2027-01-20 | 2026-10-26 | [20 empty] | Emailed district with the Reminder for October 26 Submission
A50056 | Hwys. 175 & 175S Impvts. (Cherokee Village) (S) | 5 | 175 | 2, 2S, & 3 | Fulton & Sharp | Level Up & Chip Seal; Spot patching; 2' Shoulders | 2027-01-20 | 2026-10-26 | [20 empty] | Emailed district with the Reminder for October 26 Submission
A60064 | Jefferson Co. Line – I-40 (S) | 6 | 13 | 9 & 10 | Lonoke | Rut Mill & 1.5" Overlay | 2027-01-20 | 2026-10-26 | [20 empty] | Emailed district with the Reminder for October 26 Submission
A70046 | Pike Co. Line – Hwy. 53 (S) | 7 | 8 | 5 | Clark | 2" Mill & 1.5" Overlay | 2027-01-20 | 2026-10-26 | 2026-08-31 | 2026-09-05 | 2026-09-09 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-10-13 | 2026-10-13 | 2026-10-13 | [11 empty] | Emailed to Sharon for 3rd Review
A90052 | Hwy 102B - Walton Blvd. | 9 | 102 | 3 | Benton | 2" Mill & 2" Overlay | 2027-01-20 | 2026-10-26 | 2026-09-16 | 2026-09-22 | 2026-09-24 | 2026-09-25 | 2026-09-30 | 2026-09-30 | 2026-09-30 | [13 empty] | Emailed Bryce asking if it is ready for 3rd review @10.14.26
A00104 | Hwy. 49 Impvts. (Craighead & Greene Cos.) (S) | 10 | 49 | 2 & 3 | Craighhead & Greene | 2" Mill & 2" Overlay (Sec. 2); Level Up & Thin Overlay (Sec. 3) | 2027-01-20 | 2026-10-26 | [20 empty] | Emailed district with the Reminder for October 26 Submission
A10056 | Hwy. 49 – Hwy. 193 (S) | 1 | 193 | 1 | Cross | Level Up & Chip Seal; 2' Shoulders | 2027-03-03 | 2026-12-07
A10061 | Hwy. 284 – Hwy. 64 (S) | 1 | 306 | 1 & 2 | St. Francis & Woodruff | 1" Level Up & UTBWC; 2' Shoulders | 2027-03-03 | 2026-12-07
A30050 | E. of Texarkana – East (S) | 3 | 196 | 1 | Miller | Level Up & 2" Overlay; 2' Shoulders | 2027-03-03 | 2026-12-07
A30052 | Red River – Hope (S) | 3 | 67 | 2 | Hempstead | 2" Mill & 2" Overlay (LM 0.084-10.204); 1" Level Up & UTBWC (LM 10.204-12.079) | 2027-03-03 | 2026-12-07
AX0012 | S. of Elkins – Combs (S) | 4 & 9 | 16 | 3 & 4 | Madison & Washington | Level Up & 1.5" Overlay (Sec. 3); Level Up (Sec. 4) | 2027-03-03 | 2026-12-07 | 2026-09-02 | 2026-09-08 | 2026-09-09 | 2026-09-28 | 2026-09-30 | 2026-09-30 | 2026-10-05 | 2026-10-05 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | 2026-10-14
A50054 | Diaz – Newport (S) | 5 | 17, 18, 980 | 7, 1 & 1S, 26 | Jackson | Level Up & UTBWC (Hwy. 17); 2" Mill & 1.5" Overlay (Hwys. 18, 18S & 980); 2' Shoulders | 2027-03-03 | 2026-12-07
A60065 | Grant Co. Line – I-530 (S) | 6 | 167 | 12 | Saline | 2" Mill & 2" Overlay | 2027-03-03 | 2026-12-07
A70047 | Hwy. 79B – Hwy. 205 (S) | 7 | 79 | 4 | Ouachita | 2" Mill & 1.5" Overlay | 2027-03-03 | 2026-12-07
A80043 | Hwys. 10 & 27 Impvts. (Yell Co.) (S) | 8 | 10, 27 | 3 & 4, 9 | Yell | 2" Mill & 2" Overlay | 2027-03-03 | 2026-12-07
A90048 | SW Artillery Rd. – SW Wheatgrass Blvd. (Bentonville) (S) | 9 | 12 | 2 | Benton | 2" Mill & 2" Overlay | 2027-03-03 | 2026-12-07 | 2026-09-16 | 2026-09-22 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-30 | 2026-09-30 | [13 empty] | Emailed Bryce asking if it is ready for 3rd review @10.13.26
A00105 | Hwy. 140 – I-55 (S) | 10 | 14 | 15 & 16 | Mississippi & Poinsett | 2” Overlay (Sec. 15 LM 0.00-1.796); FDR (Sec. 21 LM 1.796-2.253 & Sec. 16 LM 0.00-9.650) | 2027-03-03 | 2026-12-07
A10062 | Hwys. 121 & 261 Impvts. (Lee & St. Francis Cos.) (S) | 1 | 121, 261 | 2, 1 & 2 | Lee & St. Francis | 1.5" Overlay; 2' Shoulders | 2027-04-14 | 2027-01-11
A10057 | Hwy. 64B – Hwy. 306 (S) | 1 | 284 | 2 & 3 | Cross & St. Francis | Level Up & UTBWC | 2027-04-14 | 2027-01-11
A10055 | Hwy. 64 – Woodruff Co. Line (S) | 1 | 49 | 6 | Cross | Thin Overlay (1") | 2027-04-14 | 2027-01-11
A20046 | Dallas Co. Line - Hwy. 167 (S) | 2 | 167 | 10, 10B &11B | Grant | Level up & UTBWC (Hwy. 167), UTBWC (Hwy. 167B) | 2027-04-14 | 2027-01-11
A40060 | Hwy. 71 – Montgomery Co. Line (S) | 4 | 270 | 2 | Scott | Level Up & 1.5" Overlay (LM 0.0-8.55); 2" Mill & 2" Overlay (LM 8.55-12.292) | 2027-04-14 | 2027-01-11
A50050 | Stone Co. Line – Brandenburg (S) | 5 | 9 | 12 | Izard | 2" Overlay | 2027-04-14 | 2027-01-11
A60067 | Little Rock – Jefferson Co. Line (S) | 6 | 365 | 12 | Pulaski | 1" Mill & 2" Overlay | 2027-04-14 | 2027-01-11
A70048 | Hwy. 7B – South (S) | 7 | 7, 167 | 2 & 1 | Union | Level Up & UTBWC (Hwy. 167 LM 18.980-19.372 & Hwy. 7 LM 0.0-2.663); 2" Overlay (Hwy. 7 LM 2.663-6.206) | 2027-04-14 | 2027-01-11
A90049 | South Mountain Rd. – North (S) | 9 | 65 | 5 & 6 | Searcy | 2" Mill & 2" Overlay | 2027-04-14 | 2027-01-11
A00102 | Hwy. 93 – East (S) | 10 | 90 | 6 | Randolph | 1.5" Overlay; 2' shoulders | 2027-04-14 | 2027-01-11
A20045 | Hwy. 133 – Hwy. 82 (S) | 2 | 52 | 0 | Ashley | Mill & Overlay | 2027-05-19 | 2027-02-22
A30053 | S. of Ogden - S. of Ashdown (S) | 3 | 71 | 4 | Little River | UTBWC | 2027-05-19 | 2027-02-22
A50055 | Hwy. 11 – Kensett (S) | 5 | 385 | 0 | White | Level Up & Chip Seal w/ patching; 2' Shoulders | 2027-05-19 | 2027-02-22
A60069 | Shady Grove Rd. – Hwy. 270B | 6 | 128 | 10 | Garland | 2" Mill & 2" Overlay | 2027-05-19 | 2027-02-22
A70051 | Gurdon - Nevada Co. Line (S) | 7 | 53 | 1 | Clark | UTBWC | 2027-05-19 | 2027-02-22
A90036 | N. of I-49 - Missouri State Line (Bella Vista) (S) | 9 | 71 | 19 | Benton | 1" Level Up & UTBWC | 2027-05-19 | 2027-02-22
A90047 | S. of Hwy. 206 – Hwy. 123 (S) | 9 | 65 | 2 & 3 | Boone & Newton | Mill & Overlay | 2027-05-19 | 2027-02-22
A00101 | Piggott – Marmaduke (S) | 10 | 49 | 1 & 2 | Clay & Greene | Level Up & UTBWC, Spot Patching (Sec 1 LM 0.0-13.638); UTBWC, Spot Patching (Sec. 1 LM 13.638-15.556 & Sec. 2) | 2027-05-19 | 2027-02-22
090735 | Oklahoma State Line – East (Siloam Springs) (S) | 9 | 412 | 1 | Benton | 2" Mill & 2" Overlay | 2027-05-19 | 2027-02-22

## Stage Reference
Sequence | Review Phase | Milestone Column Header | Next Expected Milestone | Turnaround Days (Optional)
1 | 1st Review | 1st Review Sent to SB | 1st Review Returned from SB
2 | 1st Review | 1st Review Returned from SB | 1st Review Sent to District
3 | 1st Review | 1st Review Sent to District | 1st Review Returned from District
4 | 1st Review | 1st Review Returned from District | 2nd Review Sent to SB
5 | 2nd Review | 2nd Review Sent to SB | 2nd Review Returned from SB
6 | 2nd Review | 2nd Review Returned from SB | 2nd Review Sent to District
7 | 2nd Review | 2nd Review Sent to District | 2nd Review Returned from District
8 | 2nd Review | 2nd Review Returned from District | 3rd Review Sent to SB
9 | 3rd Review | 3rd Review Sent to SB | 3rd Review Returned from SB
10 | 3rd Review | 3rd Review Returned from SB | 3rd Review Sent to District
11 | 3rd Review | 3rd Review Sent to District | 3rd Review Returned from District
12 | 3rd Review | 3rd Review Returned from District | 4th Review Sent to SB
13 | 4th Review | 4th Review Sent to SB | 4th Review Returned from SB
14 | 4th Review | 4th Review Returned from SB | 4th Review Sent to District
15 | 4th Review | 4th Review Sent to District | 4th Review Returned from District
16 | 4th Review | 4th Review Returned from District | Submittal to SB for CCD
17 | Final Reviews | Submittal to SB for CCD | Requested Title Sheet
18 | Final Reviews | Requested Title Sheet | Received Signed Plans
19 | Final Reviews | Received Signed Plans | Sent to CCD
20 | Final Reviews | Sent to CCD | CCD Corrections